## Actions 2016-17
Issue No | Issue | Date added | Owner | PDWG Action | Target close out date | Open/Closed | Outcome | Comments | Moved to 2018
1 | Working Group - Scope of Engagement | 2016-08-04 | Paul Brown | Agreed at 1/3/17 meeting | 2017-03-01 | Closed | Issued | Final version issued with 1/3/17 meeting minutes | No
2 | Working Group - Funding of Managerial Duties | 2016-08-04 | TBC | Discuss with Highways England | TBA | Open |  | TBA | Yes
3 | Update of IAN 105/17 - HE yet to issue | 2016-08-04 | Mark Lamport | JB has indicated IAN 105 will be incorporated within a new SMS. | Ongoing | Open | New SMS being developed | JB attended 20/12/17 meeting and is developing SMS - IAN 105 on hold - potential link to ADMM via AIG being explored. DP looking to set up meeting | Yes
4 | Raising the Bar 26 - 5YP Action 58 | 2016-08-04 | Doug P | LW has provided draft update on 20/12 - Task Group to reconvene | Ongoing | Open |  | Latest draft issued by Lucy Wickham of WSP will including Human Factors - Task Group to meet | Yes
5 | 5 Year Plan | 2016-08-04 | David Townsend / Karl Brooks | PDWG to support delivery of 5 year plan | Ongoing | Open |  | 5YP - PDWG looking at Action 9, 58 / 88, and 123. Link up with KB over Action 56 | Yes
6 | Improve Links with AIG | 2016-08-04 | Doug Potter | Promote capture of H&S data within databases | 2016-11-24 | Closed | Links established | Meeting with Salford Uni/AIG/IAMIS/HE BIM on 24/11/16. DP working with AIG | No
7 | IAM IS Development - Integrate H&S | 2016-08-04 | Doug Potter | Promote development of H&S Database as part of IAM IS role out and integrate with BIM Asset Models | 2017-03-01 | Closed |  | DP promoted Link with IAN 182 Continue to work with AIG/IAM IS/IBI/Area 12 to improve data capture | No
8 | IAN 182 Major Scheme - Handover into Operation and Maintenance - update | 2016-08-04 | Doug Potter | Task Group have provided feedback to IAN 182 team | 2017-02-28 | Closed | Feedback provided | Feedback provided on 28/2/17 | No
9 | Maximise the benefits of BIM to deliver Health and Safety Benefits How would the model be updated? Was there a danger of accidental data deletion? Level of accuracy? Who would have access? Was there a hierarchy of governance? Where is the model stored and who maintains it? Could new data be easily added? What types of data could be stored? Can as built drawings be produced from the model? Do maintainers have the correct software and hardware to access and use the model efficiently? Standardising hazard referencing – was this included within the recently updated IAN 184/16? How accessible will the asset models be using remote technology for asset inspection, accident investigation etc.? How much of a culture change is required in the adoption of BIM? How would BIM models interface with Highways England database system and the developing IAM IS system? How were security issues addressed? | 2016-08-04 | Doug Potter | Assist in developing a joined up approach across Highways England in the development of BIM in respect to H&S | TBC | Closed | Link with IAN 182 established - PD fundemental to development of PIM models - promoted hazard data capture within PIM | IAN 182 BIM Links - PIM- PD Meeting took place at Salford Uni/AIG/IAMIS/HE BIM on 24/11/16. DP working with HE BIM team to develop BIM Action plan | No
10 | Link with BIM HE Community of Practice | 2016-08-04 | Doug Potter | Link with Emma Codrington established to promote H&S benefits of BIM | 2016-09-20 | Closed | DP attends and has good relationship with HE BIM team | DP attends HE BIM Community. Will provide regular feedback | No
11 | Align with Rail sector initiative - Safety by Design | 2016-08-04 | Tim Goddard? |  | TBC | Open |  |  | Yes
12 | IAN 105 Asset Data Flowchart | 2016-08-04 | Muneer Akhtar | Issue to Working Group for Review | 2016-10-12 | Closed | No further comments |  | No
13 | 5 year plan -Action 88 develop H&S KPI | 2016-10-12 | David Townsend | Group to develop potential KPI | 2016-12-07 | Closed | Comments to be passed to DT | Feed back to be provided from 7/12/16 meeting. | No
14 | Near Miss Designer Feedback | 2016-10-12 | Doug Potter | M1 J28-35a to look at Near Miss reporting | Ongoing | Open |  | Ongoing - DP | Yes
15 | Project Control Framework | 2016-10-12 | Paul Brown | Task Group have met with Rick Marsh and Jeremy Bird | Ongoing | Open |  | PB provided update at 6/9 PDWG - PB to review way forward | Yes
16 | Safety Wheel Questionaire | 2016-10-12 | Andy Stocks | Could this be distributed within the design community | TBC | Open |  | Discuss at next meeting | Yes
17 | IAN 63 Asbestos Management | 2016-12-07 | John Towndrow | Task Group meeting taken place | Ongoing | Open |  | JT to confirm if leading group going forward. LS provided update at 7/6 with regard to HE actions | Yes
18 | IAN 184 CAD Standards | 2016-12-07 | Doug Potter | BIM SMP Peer to peer group input | Ongoing | Open |  | DP sits on P2P Subgroup | Yes
19 | IAN 191 Safety Governance | 2016-12-07 | TBC | How to progress | TBC | Open |  | Discuss at next meeting | Yes
20 | PAS 1192 Part 6 H&S | 2016-12-07 | Andrew Finch | Comments provided | TBC | Open |  | Andrew Finchprovided feedback at meeting of 6/9 - document to be issued in the autumn | Yes
21 | DMRB Update | 2016-12-07 | TBC | Confirm PDWG input into the update | TBC | Open |  | Presentation given at 7/12/16 meeting 105 subgroup now working with DMRB update team on 105 update. Workshop due shortly | Yes
22 | Link to CIRIA Lean Initiative | 2017-02-28 | Doug Potter | PDWG have provided feedback. TG attending workshop on 15/6 | 2017-06-15 | Closed | Comments added to guide | Feedback provided to CIRIA Group | No
23 | Input into HE H&S KPI? | 2017-02-28 | Dave Townsend | Presentation provided - Andrew F to provide update | 2017-09-06 | Open |  | DT provided presentation 7/6 . AF provided update from work on A1iN at 6/9 workshop. Draft document issued | Yes
24 | Human Factors PCF | 2017-06-01 | Pav Singh | Barry D presented | 2017-09-06 | Open |  | Barry Davis presented at 6/9 workshop. PCF document still in development | Yes
25 | Temporary Works Design | 2017-06-01 |  |  | 2017-12-12 | Open |  | Ray Filips to present at 12/12 | Yes
26 | Lean For H&S | 2017-06-01 | Doug Potter | Presentation with CIRIA team to be organised | 2017-09-06 | Open |  | Potential presentation on 12/12 | Yes
27 | Link to CIRIA Lean Initiative | 2017-07-15 | Doug Potter | Attendance at Workshop | 2017-11-30 | Open |  | Invite expected | Yes
28 | Whole Life Design sub-group | 2017-07-15 | Dave Garton/Andrew F | Sub Group to be set up | TBC | Open |  | First meeting taken place 26/9. Terms of reference to be drawn up | Yes
29 | Highways England H&S File and Additional Duties | 2017-07-15 | Mark Lamport | Workshop set up | 2017-09-06 | Open |  | Feedback required | Yes

## Actions 2018
Issue No | Issue | Date added | Owner | PDWG Action | Target close out date | Open/Closed | Outcome | Comments | Moved to 2019
2 | Working Group - Funding of Managerial Duties | 2016-08-04 | TBC | Discuss with Highways England | TBA | Closed | No funding currently available | Now closed | No
3 | Update of IAN 105/17 - HE yet to issue | 2016-08-04 | Mark Lamport - Ian Scott | IAN 105 will be updated. | March 18? | Open | IAN 105 being updated and issued Spring 2019 | KEY Objective Part of new CDM Procedures - Ian Scott leading JB attended 20/12/17 meeting and is developing SMS - IAN 105 on hold - potential link of H&S File to ADMM via AIG being explored. | Yes
4 | Raising the Bar 26 - 5YP Action 58 | 2016-08-04 | Paul Brown | LW has provided draft update on 20/12 - Task Group to reconvene | Ongoing | Open | Linked to IAN69 | Paul B is coordinating Latest draft issued by Lucy Wickham of WSP will including Human Factors - Task Group to meet | Yes
5 | 5 Year Plan | 2016-08-04 | David Townsend | PDWG to support delivery of 5 year plan | Ongoing | Closed | Now Home Safe and well to be launched in Sring 2019 | 5YP - PDWG looking at Action 9, 58 / 88, and 123. Link up with DT | No
11 | Align with Rail sector initiative - Safety by Design | 2016-08-04 | Tim Goddard | Invite NR Rep | 2019-01-01 | Open | Network Rail representation | Presentation to be given at future meeting | Yes
14 | Design Change / Near Miss Designer Feedback | 2016-10-12 | Doug Potter | Procedure now in place | Ongoing | Closed |  | Ongoing - DP | No
15 | Project Control Framework | 2016-10-12 | Paul Brown | Task Group have met with Rick Marsh | Ongoing | Open |  | Agree way forward | Yes
16 | Wheel Questionaire | 2016-10-12 | Andy Stocks | Need to understand current status | TBC | Closed |  | Discuss at next meeting | No
17 | IAN 63 Asbestos Management | 2016-12-07 | TBC - Leventia Stoiou? | LV provided update at meeting of 20/12/17 | Ongoing | Open | New guide in production | Aebestos Management Procedures being updated. LV to confirm what support is required from PDWG | Yes
18 | IAN 184 CAD Standards | 2016-12-07 | Doug Potter | BIM SMP Peer to peer group input | Ongoing | Closed |  | DP sits on P2P Subgroup - DP to confirm current situation | No
19 | IAN 191 Safety Governance | 2016-12-07 | TBC | John Stock presented to PDWG in June 17 | TBC | Closed | Now GG104 | Presentation given at October 18 meeting | No
20 | PAS 1192 Part 6 H&S | 2016-12-07 | Andrew Finch | Comments provided by PDWG | 2018-03-30 | Closed | Issued February 2018 | Final document currently under review - due out in March 18 | No
21 | DMRB Update | 2016-12-07 | TBC | Presentation given at 20/12/17 PDWG | 2020-03-30 | Open |  | Presentation on progress 24/01/19 | Yes
23 | Input into HE H&S KPI? | 2017-02-28 | Dave Townsend | Update required will this now link to RtB 26 | TBC | Closed |  | Now linked to RtB 26? | No
24 | Human Factors PCF | 2017-06-01 | Pav Singh | Barry D presented | TBC | Open |  | Barry Davis presented at 6/9/17 workshop. PCF document still in development | Yes
25 | Temporary Works Design | 2017-06-01 | Pav Singh | Jim Tod presented Ray Filips presented | For Information | Open | TWf link now established - PS attending and link with H&S Hub established | Jim Tod attended at 24/01/19 Link to be established with Design Change Process Ray Filips presented at PDWG on 20/12/17 - encourage all to join Temp Works Forum | Yes
26 | Lean For H&S | 2017-06-01 | Doug Potter | CIRIA presented at May 18 WG Lean Workshop at 23/10/18 |  | Open | Lean Workshop - actions | KEY Objective Develop common list of terms | Yes
27 | Link to CIRIA Lean Initiative | 2017-07-15 | Doug Potter | Attendance at Workshop | TBC | Closed |  | See 26 - feedback mechanism to be determined | Yes
28 | Whole Life Design sub-group | 2017-07-15 | Andrew F | Sub Group set up | Ongoing | Open | List of meetings for 2019 issued | Agenda in place | Yes
30 | Maximising Benefits of BIM | 2018-01-01 | Doug Potter | Promote benefits of BIM to deliver improved H&S | Ongoing | Open | Improve links between GIS and BIM | KEY Objective Retain links with SMP/BIM Peer to Peer Groups to promote BIM best practice | Yes
31 | Risk Management | 2018-01-01 | Pav Singh | Standardise Risk Management | Ongoing | Open | Expand on Worshop outputs | Workshop took place on 21/01/2019 - PS to develop further | Yes
32 | Capture Risk Management from other sectors | 2018-01-01 | PS? | Share best practice from other sectors | 2019-09-13 | Open |  | PDWG 13 to focus on this | Yes
33 | Highways England CDM Audit process | 2018-01-01 | Doug Potter | DSAT Process now in place | Ongoing | Open | DSAT forms part of CDM Procedures | Arrange Future presentation | Yes
34 | Improve Contractor Feedback processes | 2018-01-01 | Paul Brown | Improve feedback from Safety Hub and Safety Alertsn | Ongoing | Open | Link with H&S Hub | Link to WLD Sub Group? | Yes
35 | Home Safe and Well | 2019-01-24 | Richard Wilson | Assist Introduction | Spring 2019 | Open | Work with HE |  | Yes
36 | Design Change Process | 2018-04-10 | Tim Goddard | Linked to capture of actions from Safety Alerts, Near Misses and Lessons Learned | Ongoing | Open | Provide feedback at WLDSSG | Feed back at PDWG | Yes

## Actions 2019
Issue | Date added | Owner | PDWG Action | Target close out date | Open/Closed | Outcome | Comments | Moved to 2019
Update of IAN 105/17 - HE yet to issue | 2016-08-04 | Mark Lamport - Ian Scott | IAN 105 will be updated. | 2020-02-15 | Closed | IAN 105 being updated and replaced with new CDM Standards as part of DMRB update. Draft documents now available. Intended issue early 2020. | KEY Objective Part of new CDM Procedures - Ian Scott leading JB attended 20/12/17 meeting and is developing SMS - IAN 105 on hold - potential link of H&S File to ADMM via AIG being explored. | Yes
Raising the Bar 26 - 5YP Action 58 | 2016-08-04 | Paul Brown | LW has provided draft update on 20/12 - Task Group to reconvene | PB is updated - now released | closed | GD304 Now issued - Discussed at PDWG 13 | KEY Objective Issued PD's to ensure adoption | Yes
Align with Rail sector initiative - Safety by Design | 2016-08-04 | Tim Goddard | Invite NR Rep | Actioned | closed | Network Rail now have representation | Presentation to be given at future meeting | Yes
Project Control Framework | 2016-10-12 | Paul Brown | Task Group have met with Rick Marsh | Ongoing | Open |  | Agree way forward | Yes
IAN 63 Asbestos Management | 2016-12-07 | TBC - Leventia Stoiou? | LV provided update at meeting of 20/12/17 | Ongoing | Open | New guide in production | Asbestos Management Procedures being updated. LV to confirm what support is required from PDWG | Yes
DMRB Update | 2016-12-07 | Dave Townsend | Presentations given at 20/12/17 and 24/01/19 | 2020-02-15 | Open | Now linked to update of CDM Standards | Key Objective | Yes
Human Factors PCF | 2017-06-01 | Ian Scott | Barry D presented Ian Scott to investigate status | TBC | Open |  | Pav is speaking with HF Leads Barry Davis presented at 6/9/17 workshop. PCF document still in development | Yes
Temporary Works Design | 2017-06-01 | Pav Singh | Now linked to Hub webpage Jim Tod presented Ray Filips presented | Ongoing | closed | Link with Risk Management Task Group TWf link now established - PS attending and link with H&S Hub established | JT presented BS 5975 update at PDWG 13 Link with Hub page established Link with Risk Management being established Jim Tod attended at 24/01/19 Link to be established with Design Change Process Ray Filips presented at PDWG on 20/12/17 - encourage all to join Temp Works Forum | Yes
Lean For H&S | 2017-06-01 | Doug Potter | CIRIA presented at May 18 WG Lean Workshop at 23/10/18 | 2019-05-16 | Closed | See Action 20 | KEY Objective Develop common list of terms | Closed
Whole Life Design Task Group | 2017-07-15 | Andrew F | Sub Group set up | Ongoing | Open | List of meetings for 2019 issued | Agenda in place - Design Manual in production | Yes
Maximising Benefits of BIM | 2018-01-01 | Doug Potter | Promote benefits of BIM to deliver improved H&S | 2019-05-16 | Closed | See Action 20 | KEY Objective Retain links with SMP/BIM Peer to Peer Groups to promote BIM best practice | Closed
Risk Management | 2018-01-01 | Pav Singh | Standardise Risk Management | 2019-05-16 | Closed | See Action 19 | Workshop took place on 21/01/2019 - PS to develop further | Closed
Capture Risk Management from other sectors | 2018-01-01 | TBC | Share best practice from other sectors | 2019-09-13 | Closed | See Action 19 | PDWG 13 to focus on this? | Closed
Highways England CDM Audit process | 2018-01-01 | Ian Scott | DSAT Process being incorporated with CDM roll out | 2019-08-01 | closed | DSAT forms part of CDM Procedures | Arrange Future presentation | Yes
Improve Contractor Feedback processes | 2018-01-01 | Paul Brown | Improve feedback from Safety Hub and Safety Alerts | Ongoing | Open | Link with H&S Hub | Link to WLD Sub Group | Yes
Home Safe and Well | 2019-01-24 | Richard Wilson | Assist Introduction | Launched | Open | Presentation at PDWG 14 - link now with SCSLG | Launched in June - feedback requested at PDWG 13 | Yes
Application of Lessons Learned and Design Change Process | 2018-04-10 | Tim Goddard | Process Implemented Linked to capture of actions from Safety Alerts, Near Misses and Lessons Learned | Ongoing | Open | Now updated TG presenting at PDWG 14 - link to SCSLG Feedback provided at WLDTG | KEY Objective Proposal to make Application of Lessons Learned - Catagories identified TG/DP developing - presented at PDWG 13 | Yes
Eliminating Risk from the Outset Task Group | 2019-05-16 | TBC | Task group to come together to improve sector H&S Risk Management Processes building on the work of Pav Singh | Initial outputs 20/10/2019 | Open | DP to develop TG | KEY Objective PS presented at PDWG 13 - aim to set up TG - discuss at PDWG 14 Build on RM presentations at APS Conference in September RW to approach potential chair - volunteers to be sought for the group | New
Lean and BIM Development Task Group? | 2019-05-16 | TBC | Task group to come together to improve sector Lean and BIM H&S Delivery - building on the work of Pav Singh and Arcadis/Arup and Jacobs | Initial outputs 20/10/2019 | Open | Link with 19 | PS presented at PDWG 13 - aim to set up TG. Digital improvements - Arcadis/Arup/Jacobs to provide lessons learned etc to share RW to approach potential chair - volunteers to be sought for the group | New
H&S Hub Webpage - Safe by Design section - produce Action plan | 2019-05-16 | Pav Singh | PS to produce Action Plan PDWG members to sign up to contribute discipline specific good practice examples etc. Link also with WLDTG | 2020-01-16 | Open | DA to present on HUB webpage at PDWG 15 - | KEY Objective DA to present on 16/01/20 | New
Supply Chain Safety Leadership Group | 2019-10-17 | Richard Wilson | Link with Lesley Waud - Design and Finsih initiatives | 2020-01-16 | Open | LW presented at PDWG 14 | KEY Objective Link established with Task and Finish Groups Accident Investigation - TG Excavations and Temp Works - JT | New
RTB 26 Update |  | Paul Brown | On hold? |  | Open
Stats Management | [6 empty] | Chris Gee has been appointed as Stats and Utilities coordinator - role is being developed
TwF - Sharing of Sa/Near Misses

## Action 2020
Issue | Date added | Owner | PDWG Action | Target close out date | Open/Closed | Outcome / Achievements | Comments | Moved to 2020 | Move to 2021
Project Control Framework | 2019-11-29 | Ian Scott/ Paul Brown | 1. PCI format to be updated as part of new CDM standards - change in PCF Stage updates also required 2. Ditto HSF (Vol 2) update ? 3. F10 PCF Stage issue 4. New Handover document to be created Vol 1 to 7 excluding 2? | 2020-03-30 | Open | Discuss with Richard Will be delivered in part when new CDM P&P launched in 2021 | Agree way forward with RW - | Yes | Yes
GG105 /IAN 63 Asbestos Management | 2019-11-29 | Ben Sadka | Assist Launch of GG105? | TBC | Open | Audit taken place, RACI chart now in place | Launch 2021 | Yes | Yes
DMRB Update - Replacement of IAN 105 | 2019-11-29 | Dave Townsend / Mark Lamport | Issue of new CDM Standards - DMRB Working Group to form | TBC | Open | GG106 in development and feedback has been provided on the initial draft from PDWG- move to 2021 | Key Objective : DT is to form DMRB Working Group - names supplied to DT | Yes | Yes
Human Factors PCF | 2019-11-29 | Pav Singh | Barry D presented in 2017 - PCF potentially in development - appears to have stalled Operational Concept Report shared / HF being adopted on LTC | TBC | Open | TBC | Pav to feed back on latest developments | Yes | ??
Whole Life Design Task Group | 2019-11-29 | Andrew F | Sub Group set up | 2020-01-15 | Open | Martin Partington is to set up follow-on group to build on the previous Whole Life Safety outputs of 2020 | Design Manual to be developed by January 2020 Issued in March | Yes | Yes
Improve Contractor Feedback processes | 2019-11-29 | Tim Goddard | Link with Supply Chain Safety Leadership Group | TBC | Open | Link Established with SCSLG and H&S Hub through Mark Bridges - PDWG leads set up to T&F Groups | Tim Goddard has joined Accident T&F Group - looking to promote better Root Cause Analysis Jim Todd has joined TW and Excavations T&F Group | Yes | Yes
Home Safe and Well | 2019-11-29 | Richard Wilson | Launched June 2019 Now embedded in RIP H&S Forum PDWG to provide support | Launched | Open | Presentation at PDWG 14 17/10/19 - link now with SCSLG - being led by HE with feedback to supply chain | Presentation at PDWG 14 17/10/19 - link now with SCSLG - being led by HE with feedback to supply chain | Yes | Yes
Application of Lessons Learned and Design Change Process | 2019-11-29 | Tim Goddard | Process Implemented Linked to capture of actions from Safety Alerts, Near Misses and Lessons Learned Promote improved Root cause analysis and LL capture | Ongoing | Open | Link with Stewart Evans set up Tim Goddard to work with Stewart to help improve AIRSweb Reporting (GG128) system | KEY Objective TG presented at PDWG 14 - and has joined Accident T&F G which is promoted by SCSLG Feedback provided at WLDTG | Yes | Yes
Eliminating Risk from the Outset Task Group | 2019-11-29 | Toria Thomas | Task group to come together to improve sector H&S Risk Management Processes building on the work of Pav Singh | Initial outputs 16/04/2020 | Open | Memo issued in June Action with Mike Boyland and Mike Wilson | KEY Objective PS presented at PDWG 13 - aim to set up TG - discuss at PDWG 14 Build on RM presentations at APS Conference in September RW to approach potential chair - volunteers sought for the group | New | Yes
Lean and BIM Development Task Group? | 2019-11-29 | Mark Lamport | Task group to come together to improve sector Lean and BIM H&S Delivery - building on the work of Pav Singh and Arcadis/Arup and Jacobs | Initial outputs 16/04/2020 | Open | Meetings have taken place with Jason Glasson, Andrew Smith, Neal Symmons and Sarah Bull of OD to improve Asset Data management and Handover to OD Mark Lamport to set up Group to work with the above | PS presented at PDWG 13 - aim to set up TG. Digital improvements - Arcadis/Arup/Jacobs to provide lessons learned etc to share RW to approach potential chair - volunteers to be sought for the group | New | Yes
H&S Hub Webpage - Safe by Design section - produce Action plan | 2019-11-29 | Mark Bridges | PS to produce Action Plan PDWG members to sign up to contribute discipline specific good practice examples etc. Link also with WLDTG | 2020-01-16 | Open | Link with H&S Hub webpage now well established which captures PDWG outputs and links with SCSLG etc | KEY Objective DA to present on 16/01/20 | New | Ongoing
Supply Chain Safety Leadership Group | 2019-11-29 | Richard Wilson | Link with Lesley Waud - Design and Finish initiatives PDWG to promote sharing of best practice | 2020-01-16 | Open | Link Established with SCSLG and H&S Hub through Mark Bridges - PDWG leads set up to T&F Groups | KEY Objective Link established with Task and Finish Groups Accident Investigation - TG Excavations and Temp Works - JT | New | Ongoing
RTB 26 Update | 2019-11-29 | Paul Brown | Early draft update produced Currently on hold pending feedback from Mark Byard | TBC | Open | Discussions ongoing with SCSLG as to how this will be taken forward Current PDWG advise is that it should be updated | Early draft developed and TG volunteers have been contacted - awaiting feedback from HE as to how this will be taken forward | 2020 | Clarify
Stats Management | 2019-11-29 | Mark Lamport | Improved Coordination of Stats within HE Works |  | Open | 1. PDWG have now a well established link with Chris Gee to provide support where required through Mark L 2. PDWG supported the update of RtB 9 | Chris Gee has been appointed as Stats and Utilities coordinator - role is being developed | New | Ongoing
TwF - Sharing of Safety Alerts/Near Misses | 2019-11-29 | Jim Todd | Improve capture of TW outputs on Safety Alerts and Near Misses to assist development of improved permanent works design |  | Open | DP has been working closely with JT to 1. Improve links 2. Provided feedback on the Constructability Report from PDWG and ongoing feedback 3. Capture potential improvements in TW links with HE 4. Promote a Carbon Capture piece | DP to speak further with JT to see if a process can be introduced here | New | Ongoing

## Actions 2021
Issue | Date added | Owner | PDWG Action | Target close out date | Open/Closed | Outcomes | Comments | Move from 2020
Project Control Framework | 2019-11-29 | Ian Scott/ Paul Brown | 1. PCI format to be updated as part of new CDM standards - change in PCF Stage updates also required 2. Ditto HSF (Vol 2) update ? 3. F10 PCF Stage issue 4. New Handover document to be created Vol 1 to 7 excluding 2? | 2021-03-30 | Open | Launch imminent | HSMS is currently being updated. This includes 1. New CDM Standards - date to be confirmed 2. New Asbestos Supporting Doc. Exp April 21 | Yes
GG105 /IAN 63 Asbestos Management | 2019-11-29 | Ben Sadka | Assist Launch of GG105 - Launched in Jan 2020 | TBC | Open | TBC | RW to consider what inputs required from PDWG Linked to 2 above | Yes
DMRB Update - Replacement of IAN 105 | 2019-11-29 | Dave Townsend / Mark Lamport | Issue of new CDM Standards - DMRB Working Group to form GG106 in development and feedback has been provided on the initial draft from PDWG- move to 2021 | 2021-03-30 | Open | Launch imminent | Key Objective : DT to determine way forward and how will this link with SCSLG, H&S Hub and PDWG | Yes
Human Factors PCF | 2019-11-29 | Pav Singh | Barry D presented in 2017 - PCF potentially in development - appears to have stalled Operational Concept Report shared / HF being adopted on LTC | TBC | Open | TBC | Pav to feed back on latest developments Linked to LTC and A303 Tunnelling | Yes
Whole Life Design Task Group | 2019-11-29 | Martin Partington | Martin Partington is to set up follow-on group to build on the previous Whole Life Safety outputs of 2020 | TBC | Open |  | MP to re-establish the group and target issue of further Safety Alert LL Review what is already on the Hub - are people using them do they know where they are | Yes
Improve Contractor Feedback processes | 2019-11-29 | Mark Bridges | Link with Supply Chain Safety Leadership Group through Mark Bridges | Ongoing | Open |  | PDWG representatives are in place for the majority of SCSLG T&F Groups Ensure PDWG Leads are embedded with Safety HUB T&F Groups to provide support | Yes
Home Safe and Well | 2019-11-29 | Richard Wilson | Launched June 2019 Now embedded in RIP H&S Forum PDWG to provide support | Launched | Open | Ongoing | RW to confirm objectives for 2021 RW to share actions - PDWG 20 | Yes
Application of Lessons Learned and Design Change Process | 2019-11-29 | Tim Goddard | Process Implemented Linked to capture of actions from Safety Alerts, Near Misses and Lessons Learned Promote improved Root cause analysis and LL capture | Ongoing | Open | Link with Stewart Evans set up Tim Goddard to work with Stewart to help improve AIRSweb Reporting (GG128) system | KEY Objective TG to link with Stewart Evans and provide support following SE presentation at PDWG 19 - Working Group now in place SE AIRSweb Link with PDWG to be developed | Yes
Eliminating Risk from the Outset Task Group | 2019-11-29 | Mike Boyland | Memo issued in May 2020 Action with Mike Boyland and Mike Wilson | TBC | Open |  | KEY Objective Agree way forward | Yes
Digital Asset Management - Lean and BIM Development Task Group? | 2019-11-29 | Mark Lamport | Meetings have taken place with Jason Glasson, Andrew Smith, Neal Symmons and Sarah Bull of OD to improve Asset Data management and Handover to OD Mark Lamport to set up Group to work with the above | TBC | Open |  | Key Objective Jason Glasson presented at PDWG 19 - further support from PDWG via Mark Lamport to be identified Link to be developed with Sarah Bull | Yes
H&S Hub Webpage - Safe by Design section | 2019-11-29 | Dave Avery | Link with H&S Hub webpage now well established which captures PDWG outputs and links with SCSLG etc | Ongoing | Open |  | DA to work with Phil Farrah to maintain webpage | Ongoing
Supply Chain Safety Leadership Group | 2019-11-29 | Mark Bridges | Link Established with SCSLG and H&S Hub through Mark Bridges - PDWG leads set up to T&F Groups | Ongoing | Open |  | KEY Objective Links established with Task and Finish Groups Accident Investigation - TG Lost Loads - MB Mental Health - DA RtB 26 - PB Safety by Design - AF Utilities Avoidance - ML Incursions and IPV's - DA Passport Scheme - DA GI and Archaeology - RW | Ongoing
RTB 26 Update | 2019-11-29 | Paul Brown/ Mark Bridges | Discussions ongoing with SCSLG as to how this will be taken forward Current PDWG advise is that it should be updated | TBC | Open |  | Key Objective Early draft developed and TG volunteers have been contacted - awaiting feedback from HE as to how this will be taken forward MB has provide a second draft and this has been issued to PDWG for comment (18/1/21). PB will capture feedback and work with MB to finalise. | Yes
Stats Management | 2019-11-29 | Mark Lamport | Improved Coordination of Stats within HE Works 1. PDWG have now a well established link with Chris Gee to provide support where required through Mark L 2. PDWG supported the update of RtB 9 | Ongoing | Open |  | Understand support required for Chris Gee Spotlight Workshops on H&S topics are being run - this includes a Stats workshop with OD etc to highlight all the various initiatives | Ongoing
TwF - Sharing of Safety Alerts/Near Misses | 2019-11-29 | Jim Tod | Improve capture of TW outputs on Safety Alerts and Near Misses to assist development of improved permanent works design 1. Improve links 2. Provided feedback on the Constructability Report from PDWG and ongoing feedback 3. Capture potential improvements in TW links with HE 4. Promote a Carbon Capture piece | Ongoing | Open |  | Agree synergies with TwF | Ongoing