## Sheet1
Subject | Tile / Reference | Actions / Findings for Arcadis | Designer/PD Implications | Lesson Learnt
Incursions | 18-01 MSM Safety Briefing - Incursions | Record any incursion incident. Follow the procedure. I have a comment about one of the process elements. | TM is not permanent works design element, however thought about entry and exit of the works from live carriageway should be considered in the design process and the location of these particularly at junction intersections where driver confusion is a possibility
Lantern covers falling from luminaires | HEi042 | luminaires with this cover to be removed from designs on Smart Motorways going forward | check on RIP and NIP schemes re use of these luminaires currently under review internally if on a smart motorway or all lane running project it s decided by the client to keep existing lighting rather than replace with new, to identify and mitigate any risks and flag up to the client the risks.
High Potential Near Miss | Hei059 High Potential Near Miss | Failure of design/ check system - designers/ maintainers. Retrofit? The (non-structural?) 'designer' of the additional equipment should have undertaken appropriate checks/ held appropriate discussions - change control process. Has appropriate check process been followed? | Principal Designer Check designers have followed correct TAA processes Designer Structural Designers should undertake thorough check on all modifications to existing infrastructure
Principal Designer Duties | HEi062 Principal Designer Duties | PD team have drafted a response to Highways England/ Etienne. Comment from Etienne: not well written and interpretation of regulations is awry: retrofit, accident damage? New works? - New gantries here. Who are the other parties to the contract, what communication was there. Feedback - key issue is failure to properly evaluate modification of modular construction | Principal Designer Ensure designers are communicating Issue Raised at PDWG on 24/01/19 Barry O'Driscoll presented on behalf of SMP - discussed at working Group - main issues 1. Many failings 2. TAA failed 3. Modular construction not properly reviewed 4. Breakdown in communications Designers Ensure TAA processes are followed | Issues raised by Arcadis and issued back to HE on 20th Nov 2018
M1 J39-42 Smart Motorway: Pile Connection Defect | HEi071 - M1 J39-42 Smart Motorway - Pile Connection Defect | There was no material failure or collapse, but upon investigation it was evident that the top hat grub screws were no longer providing an adequate frictional connection and no lock nuts were fitted. The sign was removed and checks on all other structures mounted on this pile connection detail were immediately undertaken. It was identified that none of the top hats had lock nuts installed, and in some cases hex head bolts had been used instead of grub screws, though no further rotations or movement was identified. On review of the QITP (Quality Inspection Test Plan) and installation check sheets there was no verification that the specified grub screw torque had been applied and there was no reference to the requirement for lock nuts to be fitted. Though this particular connection detail is bespoke to M1 J39-42 Smart Motorway, the lack of understanding of the design requirements or verification records of compliance with the design is applicable to all works. | Designers • Not to assume a design detail can be upscaled to a larger item without increasing member sizes, numbers, torques etc. • Where design change occurs designers need to check suitability of fixing details. (Was a sufficiently robust check undertaken that the pile design and top hat connection detail developed for the original, smaller ROTTMS was suitable to accommodate new, larger ROTTMS?) • Design life to be considered: even with similar sized signs the permanent signage may require more robust/ different fixings.
Attachments to Lighting Columns | HEi096 - Attachments to Lighting Columns | Add to check sheet Has TAA been followed as a result of the design change | Principal Designer Ensure TA process have been followed Designer Follow TA processes | Lessons Learned: Are Area teams responsible for this? Or technology companies? There have been several previous instances of infrastructure being overloaded with additional kit. There is a lack of tracking/ record keeping for inspections undertaken by HE. In the past TECHMAC contracts have been separate from MACs - this doesn't help. This situation may have changed with the move to ASCs. Fewer interfaces are better. Engineering review needs to be undertaken before attaching additional equipment onto columns. How is this managed? PD team to escalate this to Richard Wilson. Potential for criminal liability. Budgets for maintenance/ inspection have been slashed. Details of additional equipment are not typically added to SMIS. Does SMIS have a warning system? If infrastructure is not on the SMIS register then there is nothing to flag up that a general or principal inspection is due. How does HE manage communication between different contracts? Is there are role for asset manager/ PD? Forum for review? Has any trend analysis been undertaken? As noted above the PD team is to sort alerts into categories for future reviews- this should be one such category.
Paving slab RIDDOR Incident | HEi119 - Paving slab RIDDOR Incident | Operational Excellence Team were asked to conduct a lesson learnt workshop on underbridge paving, following a RIDDOR. This slope is at a 45-degree angle. A decision had been made at design stage to pave this area with concrete paving slabs to prevent vegetation growing and deter animals from burrowing. There is a four step process involved in laying the slabs: 1. Prep 2. Slabbing 3. Finishing 4. Landscaping. The slabs are 600x600mm and weigh 42kg. The gangs lay these slabs whilst wearing harnesses, anchored at the top of the slope. The concrete slabs are laid in line with the structure and a neat line is cut the finish the slabs at the edges. Possible alternative solutions are: . - Larger Slabs – These slabs could be precast and then installed. This operation would require the use of specialised plant – policy dicates that the use of underslinging is prohibited. However, a case could be made with the correct risk assessments. There is also a challenge with headroom at the top of the slopes to sling correctly. -LPS – Due to working under structures, GPS cannot be used, however LPS and machine control could be used in the setting out and laying of the sub-base, but will still be labour intensive to lay the slabs. -Fire Retardant GRP (Glass Reinforced Plastic) – This would incur large maintenance costs and may also present a fire hazard (smoke across the carriageway etc). -Grasscrete – Lighter in weight, which would reduce the risk of manual handling accidents. Does not require grass for stability. Comes in plastic and in concrete. Reduces the level of sub-base. Rubber pellets or other materials could be used to infill. -Geo Grid – Similar to Grasscrete. This would need to be fire retardant due to the proximity to the carriage way. -Stone Pitches - Would need to be laid correctly to get the required finished. Use to match the terrain/location of the structure. Likely to be expensive if any maintenance required. -Gabion Baskets – This is an expensive solutions. Requires a lot of time and the correctly skilled people to install and fill. -Smaller Paving Slabs – This will reduce the weight of the paving slab, however this would require more slabs to be laid, and still does not address the cons highlighted above. -Spray Concrete/Shotcrete – Does not have the asthetically pleasing look. -Change of design - With a change of design, this could reduce the working at height risk by introducing mid way landings. -Concrete Canvas “Dutch Lining” – A woven mat laid from a roll with concrete sandwich in between the two layers. Does not give a good finish. -Landscaping – Currently landscaping is not used due to the lack of light and water to the area. -Reduce Paving – If paving were to be reduced, for example, pave the centre third (and not cut the slabs) and landscape the outer thirds. This would heavily reduce the risk to the gangs and save on costs. -New Material – looking at an alternative, a spray asphalt. There are companies that offer this service. Costs are undetermined to date and further research is needed. | Consideration of most appropriate underbridge paving design solution taking account of findings from the Underbridge Paving Lessons Learnt Workshop: August 2019 report issued | Lessons Learned for Arcadis: (As per previous month's discussion) Slabs weighed 42kg, is it practical to lift these manually (by one operative?) On a revetment slope the safety issue is compounded. Slabs were stored on edge, not safe or in accordance with method statement (done for speed?). Could usefully have a cradle or other mechanism to store the slabs in the temporary situation. Unrealistic time pressures may have been a factor. Was the working method challenged by the PD or PC? - not stated in safety alert. Discussed at HUB on 5th September. To be included in presentation at PDWG. These slabs have been used without problem on a number of jobs. Slabs were supposed to be mechanically laid, but there is no evidence of plant in the picture? Insufficient information. Designers appear to have specified something inappropriate - why not sprayed concrete here?
Lighting Unit dropped through Incorrect fixing | HEi132 Lighting Unit dropped through incorrect Fixing | Note lighting unit / column arm connection detail requirement. | Changes to the lanyard connection must be approved by the Designer /Manufacture and agreed with the Overseeing Organisation. | Lessons Learned for Arcadis: The connection required a full 100mm engagement due to the location of fixing bolts and the internal taper of the lantern fixing. Remedial works were required to all lighting units installed in this manner with the unauthorised detail, to provide the full 100mm connection along with re-torqueing the fixing bolts to manufacturer’s settings. • Lanyard secondary connection appears to have made things worse. Tapered joint is now unable to close fully because of the lanyard attachment point. • There have been a number of safety alerts over time involving lighting columns and street furniture. Some of these have arisen because the of equipment attached (e.g. solar panels), which places undue load on the structure or through an unapproved connection. Other alerts have arisen because of fatigue or corrosion in columns that have come to the end of their design life. Hei 137 in the current set of alerts for review is one such; there was also an issue 2-3 years back when luminaires fell from lighting columns due to fatigued connections. Also solar panels fitted to street furniture and a recent alert re. holding down bolts on matrix sign. Ther is a bit of a theme here. • Change control issue: Retrofit changes, such as attaching kit to columns and signs, should go through TA process. Changes to the lanyard connection should have been approved by the designer /manufacturer and agreed with the overseeing organisation. This doesn't appear to have happened. The maintainer has made an unauthorised change without recognising the significance of what they have done. Column/ fitting design is done by the manufacturer in most cases, not lighting designers who merely specify components from a lighting catalogue. • Do we have a lighting team? Charlie Chambers. Not TLG. Peter Trustram has been retired. Fatigue connection issue from 2 years' ago plus. Simon Langley HE lighting rep. still involved. • Bob Tuthill's safety alert database is on safety hub website is good source for locating relevant alerts.